## Bug & Test Log
ID | Date | Sprint | Area Tested | What I Did (Test Performed) | What I Found | Severity | Action Taken | Status | Retest Result
T01 | 19/05/2026 | Sprint 3 | Game launch | Opened game.html in Chrome and clicked Start Mission repeatedly | Game would not start — start button unresponsive, mission never loaded | High | Reported to Richa; start process was rebuilt; re-tested new build | Closed | Pass
T02 | 21/05/2026 | Sprint 3 | Audio | Played first level with sound on in Chrome and Edge | No engine or collision sounds — audio not triggering on user interaction | High | Reported; browser audio trigger functions implemented; verified sound cues | Closed | Pass
T03 | 23/05/2026 | Sprint 3 | Controls | Tested arrow keys and on-screen controls for lane changes | Occasional double lane change on single key press | Medium | Logged on Trello; key-press handling debounced | Closed | Pass
T04 | 26/05/2026 | Sprint 4 | Mobile play | Played full level on Android phone (Chrome mobile) | Car movement lagging badly on mobile, frame drops during obstacle waves | High | Reported; rendering and controls optimised; re-tested on same device | Closed | Pass
T05 | 29/05/2026 | Sprint 4 | Scoring & movement | Ran GameV2 build; collected coins and collided with obstacles | Score not updating correctly after collision; movement freeze (raised in 29/05 standup) | High | Discussed in standup with Sabina; scoring logic fixed in next commit | Closed | Pass
T06 | 29/05/2026 | Sprint 4 | Quiz integration | Answered quiz questions correctly and incorrectly on purpose | Correct answers sometimes gave no reward feedback | Medium | Reported; reward popup linked to quiz result | Closed | Pass
T07 | 30/05/2026 | Sprint 4 | Progress saving | Closed browser mid-game and reopened to check Local Storage save | Progress restored correctly; no issue found | Low | Documented as passed in test notes | Closed | Pass
T08 | 31/05/2026 | Sprint 4 | Difficulty levels | Played Easy, Medium and Hard back-to-back | Hard mode obstacle gap too small — nearly impossible for target age group | Medium | Raised in team chat; obstacle spawn gap widened for Hard | Closed | Pass
T09 | 01/06/2026 | Sprint 5 | Login & register pages | Created account, logged out, logged back in; tried invalid inputs | Register page accepted empty username | Medium | Reported; validation added to register form | Closed | Pass
T10 | 01/06/2026 | Sprint 5 | Leaderboard | Posted several scores from two accounts and checked ordering | Scores displayed and ordered correctly | Low | Documented as passed | Closed | Pass
T11 | 02/06/2026 | Sprint 5 | Cross-browser | Smoke test in Chrome, Edge and Firefox before deadline build | Minor layout shift on garage page in Firefox | Low | Logged; CSS fix applied by Renita | Closed | Pass
T12 | 04/06/2026 | Sprint 5 | Sound mapping | Verified sound cues against project activity (sound testing doc) | Audio events matched activity levels as designed | Low | Confirmed and recorded in Meeting 6 evidence | Closed | Pass
T13 | 05/06/2026 | Sprint 5 | Full playthrough | Final end-to-end run: register → play all 3 levels → leaderboard | No blocking issues; prototype demo-ready | Low | Signed off final build for presentation | Closed | Pass

## Summary
Testing Summary — Anjila Gurung (Tester, Road Rush Cyber Racer)
Total tests logged | 13
High severity found | 4
Medium severity found | 4
Low / passed checks | 5
Issues closed | 13
Retests passed | 13
Role context: tested builds at the end of every sprint, reported bugs to developers,
retested fixes, and signed off the final demo build (05/06/2026).